## Meeting minutes(week 2)
Data Science Project (Group 25) Weekly Meeting Minutes
Attendance Tracking | Attendees: 1 Aug: Yuki Liang (Student), Chelsea Ren (Student), Chang Wang (Student), Cam Pan (Student), Craig Lewis (Supervisor), Jess Letch (Client) | Absent with Apologies: 1 Aug: None |  | Date and Time | 1 August 2024 11am to 12pm Online
Area | Discussion Points | Next Steps | Owner | Timelines | Remarks
Dataset Exploration & Data Cleaning | 1. Experiment: apply the 'data_cleaning' function to other countries and summarise relevant issues (e.g. column not match, different response variable definition, etc.) - WIP 2. Document the key points and share with client so that we can decide the focus point of this project this sesmester, need to donule check with the client: if the Asian countries requirement is compulsory | 1. Cam and Chang to explore the data preprocessing session within other countries and share progress in the next meeting 2. FYI | Cam and Chang | 2024-08-05 | auto download the dataset
Response Variable Redefinition | Follow-ups from last client meeting Unclear Response Variable Value 1. Client suggested that the y value needs to be proportional to the severity - WIP 2. Research about the related methods and refer to paper | 1. Yuki to do research about how to reassign the y value and share progress in the next meeting 2. FYI | Yuki | 2024-08-05
Dashboard Visualisation | Key points 1. Supervisor suggested the graphs need to be more clear (for communication not exploration) 2. Need to discuss further improvement with client - WIP | 1. Need to rethink about how to express the information clearly 2. Write down the protential issue and suggestion to prepare for the client meeting | Yuki | 2024-08-05
Model Training | 1. Random Forest: computationally intensive, overfitting (78%) - DONE 2. Going to do experients on XGBoost, Naïve Bayes, Neural Networks (pros and cons in proposal FYI) - WIP | 1. FYI 2. Chelsea to apply different machine learning model and share progress in the next meeting | Chelsea | 2024-08-05
Model Comparison | 1.Record the running time for each model for computational comparison later - WIP | 1. Chelsea to visualise the result and do comparison for various models (analyse the protential reason) | Chelsea | 2024-08-05
Timeline Confirmation | 1. Need to refine the timeline as the developing time is less than our expectation, have to cut down most of the task comsuming time and prepare for the final report earlier which accounts for 70 points in the whole subject |  | All | 2024-08-05
Progress Tracking Application | 1. Better to secure an application to keep track of everyone's progress in this project (prepare for the final submission) -done |  | All | TBD
Final Report Structure Discussion | 1. Supervisor suggested us to discuss about the structure of the final report asap - was not discussed | 1. Check the criteria of final report and discuss in the next meeting 2. Someone can start to create the report and slide templates and share with the group | All | 2024-08-09
Template (Cam)
Final Report Structure Fill Out (All)

## Meeting minutes(week 4)
Data Science Project (Group 25) Weekly Meeting Minutes
Attendance Tracking | Attendees: 12 Aug: Yuki Liang (Student), Chelsea Ren (Student), Chang Wang (Student), Cam Pan (Student), Craig Lewis (Supervisor), Jess Letch (Client) | Absent with Apologies: 14 Aug: None |  | Date and Time | 14 August 2024 2pm to 2:30pm Online
Area | Discussion Points | Next Steps | Owner | Timelines | Remarks
Dataset Exploration & Data Cleaning | 1. Download the dataset of other countries - Done 2. Do the data cleaning to these data |  | Cam and Chang | 2024-08-12 | auto download the dataset
Response Variable Redefinition | 1. Reassign the Responce variable (Y): higher value represent high proportion - DONE | 1. Continue work on the responce variable of other countries | Yuki | 2024-08-12
Dashboard Visualisation | Key points 1. Share the redesign the tableau dashboard |  | Yuki | 2024-08-12
Model Training | 1. Random Forest: computationally intensive, overfitting (78%) - DONE 2. XGBoos: not suitable for response vairable - DONE 3. Naïve Bayes: handle missing values (48%), but low model accuracy - DONE | 1. FYI 2. Chelsea to apply different machine learning model for other countries and share progress in the next meeting | Chelsea | 2024-08-18
Model Comparison | 1.Record the running time for each model for computational comparison after whole data set has been cleaned - WIP | 1. Chelsea to visualise the result and do comparison for various models (analyse the protential reason) | Chelsea | 2024-08-18
Timeline Confirmation | 1. Need to refine the timeline as the developing time is less than our expectation, have to cut down most of the task comsuming time and prepare for the final report earlier which accounts for 70 points in the whole subject |  | All | 2024-08-05

## Meeting minutes(week4,internal)
Data Science Project (Group 25) Weekly Meeting Minutes
Attendance Tracking | Attendees: 16 Aug: Yuki Liang (Student), Chelsea Ren (Student), Chang Wang (Student), Cam Pan (Student) | Absent with Apologies: 16 Aug: None |  | Date and Time | 16 August 2024 4pm to 5pm Online
Area | Discussion Points | Next Steps | Owner | Timelines | Remarks
Response Variable Requantify | 1. the y value 0-never, 1-often,...9 missing, the value of the severity cannot be used directly which can cause a misestimation on severity. | 1. transfer y to a more reasonable value | Chang | 2024-08-16 | auto download the dataset
Response Variable Redefinition | 1. another solution to the above question | 1. Do one hot encoding to response variable | Yuki | 2024-08-16
Dataset Exploration & Data Cleaning | 1. Download the dataset of other countries - Done 2. Do the data cleaning to these data 3. Check to what extent the dataset from country are different form Philippine's |  | Cam | 2024-08-16

## Meeting minutes(week5,supervis)
Data Science Project (Group 25) Weekly Meeting Minutes
Attendance Tracking | Attendees: 22 Aug: Yuki Liang (Student), Chelsea Ren (Student), Chang Wang (Student), Cam Pan (Student),Craig Lewis (Supervisor) | Absent with Apologies: 22 Aug: None |  | Date and Time | 22 August 2024 3:15pm to 4pm Online
Area | Discussion Points | Next Steps | Owner | Timelines | Remarks
Work Reporting | Report the work we've done last week, detail please see meeting minutes week4 |  |  | 2024-08-22
Report Writing | 1. report writing alignment before the final submission 2. clear elabrate how we come up these idea, give readers clear logic why we do this | 1. start writing as soon as possible |  | 2024-08-22
Gitbub | add Craig to github |  |  | 2024-08-22

## Meeting minutes(week 6)
Data Science Project (Group 25) Weekly Meeting Minutes
Attendance Tracking | Attendees: 26 Aug: Yuki Liang (Student), Chelsea Ren (Student), Chang Wang (Student), Cam Pan (Student), Craig Lewis (Supervisor), Jess Letch (Client) | Absent with Apologies: 26 Aug: None |  | Date and Time | 26 August 2024 2pm to 2:30pm Online
Area | Discussion Points | Next Steps | Owner | Timelines | Remarks
Automation of data preparation & data cleaning | Completed and refined codes for automation of data preparation as follows: 1. open the DHS program website 2. log in with our account name, password 3. select our program and country 4. choose the standard DHS survey data files 5. download the individual dataset 6. unzip data file 7. create variable description CSV file for each survey dataset 8. data cleaning and combination | handle missing data, handles any differences in attributes that might exist across different datasets | Cam and Chang | 2024-08-26
Dashborad | Idea of futher steps: 1. Input all the data in Asian regions(Cam): need to add year and countryname(clean all NA rows first) 2. Display some specific attributesonly first (no need yinvolved) 3. XAttributes: Age at first forced sexual act &Urban/Rural area | Try all ideas first | Yuki | 2024-08-26
Model Training | 1. SVM: reach our highest accuracy: 80% 2. PCA: reduce 100 attributes to 25. | Apply SVM to other countries. Refined PCA futher. | Chelsea | 2024-08-26
Timeline Confirmation | 1. Need to schedule the presentation time. And maybe more collaboration in the future. | talk to our supervisor Craig first | All | 2024-08-26
Github

## Meetingminutes(week6,internal)
Data Science Project (Group 25) Weekly Meeting Minutes
Attendance Tracking | Attendees: 30 Aug: Yuki Liang (Student), Chelsea Ren (Student), Chang Wang (Student), Cam Pan (Student), Craig Lewis (Supervisor), Jess Letch (Client) | Absent with Apologies: 30 Aug: None |  | Date and Time | 30 August 2024 2pm to 2:30pm Online
Area | Discussion Points | Next Steps | Owner | Timelines | Remarks
Automation of data preparation | Automation all DONE. |  | Cam | 2024-08-30
data cleaning | Prepare data for dashborad and model training. |  | Chang | 2024-08-30
Dashborad | Idea of futher steps: 1. Input all the data in Asian regions(Cam): need to add year and countryname(clean all NA rows first) 2. Display some specific attributesonly first (no need yinvolved) 3. XAttributes: Age at first forced sexual act &Urban/Rural area | Try all ideas first | Yuki | 2024-08-30
Model Training | Apply SVM to other countries. Refined PCA futher. |  | Chelsea | 2024-08-30
Github | 1. add clients and supervisor |  |  | 2024-08-30
Final Report | Start writting in the middle of Sep. |  |  | 2024-08-30

## Week7
Data Science Project (Group 25) Weekly Meeting Minutes
Attendance Tracking | Attendees: 9 Sep: Yuki Liang (Student), Chelsea Ren (Student), Chang Wang (Student), Cam Pan (Student) | Absent with Apologies: 9 Sep: None |  | Date and Time | 9 September 2024 2pm to 3pm Online
Area | Discussion Points | Next Steps | Owner | Timelines | Remarks
Automation of Data Preparation | 1. Check the attribute name (some attribute names are not completed) 2. Download spatial data set 3. Add a filter before data cleaning to select the top X completed data attributes | Conduct EDA to confirm the value of X first Extract y first, filter X (e.g. top 100) | Cam | 2024-09-09
Data Cleaning | 1. Prepare data for dashboard and model training (both completed data and NA data) 2. Reorganize the data cleaning function (add 'try-except') 3. Summary table: record missing data attribteuteame | Add 'try-except' to catch error | Chang | 2024-09-09
Dashborad | 1. Conducted data analysis in Philippine Input all the data in Asian regions(Cam): need to add year and country name(clean all NA rows first) 2. Display some specific attributes only first (no need y involved) 3. New idea (slide) | 1. Data Size Issue 2. Education/financial background/work (stressful lifestyle) | Yuki | 2024-09-09
Model Training | 1. Apply SVM to other countries. Refined PCA further. 2. PCA may not work in this case 3. Trying to implement variable selection | Refine variable selection and wait for the 'filter' | Chelsea | 2024-09-09
Github | 1. add clients and supervisor | Add meeting minutes/code (what else do we need? Need to confirm with supervisor) | All | 2024-09-12
Final Report | 1. Start writing in the middle of Sep. 2. Refine the structure of the report |  | All | 2024-09-23
Final Presentation Time | Confirm with supervisor first |  | All | 2024-09-12

## Final Presentation Criteria
| Some ideas: | Criteria:
| Research question introduction: Problem Formulation | Introduction to the client, the data science problem and group member
| Focus stage: visualisation and model training | Data Science workflow explained/EDA included: implications discussed
| Data Analysis | Methods - justification included; description clear; mathematical rigour at the expected standard
| ML models | Results and Conclusion - valid and informative -- are the results of interest to the client/host and to the wider data science community?
| Logical progression of argument | Presentation technique: read from a script? Did the group engage with the audience? Did all group members contribute?
1 mark per min if presentation greater than 15 mins
15mins
5mins Q&A
Recording must be shared with client as well
Live Presentation

## Final Report Criteria
6k-10k words
There are two examples on LMS (refer to the length and research scope)
Subject coordinators can access our repository logs and records of all meetings (included in an appendix)
Github

## Final Report Structure
1. Introduction
2. Background/Literature review
2.1 The clent's Problem
2.2 Literature Review (Related work)
3. Data Preprocessing
3.1 Dataset Selection
3.2 Data Exploration
3.3 Data Processing
4. Dashboard Visualisation
4.1 Data insight
4.2 Dashboard Functionality
4.3 Key Findings
4.4 Suggestion
5. Data Modelling | (?PCA)
5.1 Model selection and Algorithm Defination
5.2 Results and Comaprison(Graph)
5.3 Limitations and Future Enhancements
6. Conclusion
7. Appendix